## Academic Exchange Work Plan
|  | Field | Content
Academic Exchange Work Plan for San Diego Trip |  | Project Name | Analysis and Regulation of Cognitive Neural Circuits
|  | Project No. | NSF-COG-2024-07
|  | Principal Investigator | Zhang Mingyuan
|  | Plan Date | 2024-06-28
Phase | Time | Main Tasks/Activities | Location | Person in Charge | Participants | Expected Outcomes/Goals | Status
Pre-departure Preparation | June 28 – July 17, 2024 | 1. Complete conference registration and abstract submission. 2. Prepare invited presentation slides and related display materials. 3. Confirm meeting time with US partner team (Dr. Smith, Stanford) during the conference. 4. Handle travel approval and booking procedures. | Our Institute | Zhang Mingyuan | Li Hua (Project Assistant) | 1. Registration confirmation letter. 2. Finalized presentation materials. 3. Mutually confirmed meeting agenda. 4. Completed travel approval form. | Completed
Conference Attendance & Academic Exchange | July 19 – 21, 2024 | 1. Attend the plenary sessions and "Dynamic Imaging of Neural Circuits" sub-forum. 2. On the afternoon of July 20, deliver an invited presentation titled "Working Memory Encoding Mechanisms of Prefrontal Cortex Based on Two-Photon Imaging." 3. On the evening of July 20, hold a project progress meeting with Stanford University and MIT collaboration teams to review Joint Experimental Protocol V2.0. 4. On the morning of July 21, attend the "Pre-Clinical Evaluation of Brain-Computer Interfaces" technical workshop and conduct technical consultations with equipment manufacturers. 5. Compile academic notes and exchange insights daily. | San Diego area, California, USA | Zhang Mingyuan | Zhang Mingyuan | 1. Complete academic presentation. 2. Produce "Meeting Minutes with Stanford/MIT Team." 3. Obtain technical workshop materials and preliminary equipment quotations. 4. Complete "Daily Academic Record of Conference Attendance." | In Progress
Follow-up Summary & Reporting | July 22 – 31, 2024 | 1. Organize conference materials and write a conference attendance summary report. 2. Present a special briefing to the project team and institute on frontier developments. 3. Revise the project's second-half experimental plan based on exchange outcomes. 4. Complete travel reimbursement procedures. | Our Institute | Zhang Mingyuan | All project team members | 1. "Summary Report on Attending the 12th International Neuroscience Symposium." 2. Updated Project Experimental Plan (V3.0). 3. Complete reimbursement material package. | Not Started
Role | Name | Date
Plan Reviewer | Wang Jianguo (Department Head in Charge) | 2024-06-30

## Approval
Research Project Business Travel Approval Form
Field | Content | Field | Content
Project Name | Analysis and Regulation of Cognitive Neural Circuits | Project No. | NSF-COG-2024-07
Applicant | Zhang Mingyuan | Position/Role | Professor
Accompanying Personnel | None | Purpose of Travel | Attend the 12th International Neuroscience Symposium and advance project international cooperation.
Destination | San Diego area, California, USA | Planned Travel Dates | July 18, 2024 – July 22, 2024
Main Tasks | 1. Deliver an invited presentation at the "Dynamic Imaging of Neural Circuits" sub-forum. 2. Hold a project progress meeting with Stanford University and MIT collaboration teams. 3. Attend the brain-computer interface technical workshop and conduct equipment research. 4. Conduct academic exchanges and talent engagement.
|  | Applicant Signature: Zhang Mingyuan | Date: June 25, 2024
Project Leader Opinion | The information is accurate. Approved for travel. Suggest focusing on the feasibility assessment of the joint experimental plan. | Signature: Zhang Mingyuan (self-approval) | Date: June 26, 2024
Department Head Opinion | Approved. Please strictly observe foreign affairs discipline and financial regulations, and ensure the itinerary serves the project objectives. | Signature: Wang Jianguo | Date: June 28, 2024
Finance Department Review | The budget is consistent with the project plan. Invoice requirements shall be handled in accordance with the Travel and Expense Reimbursement Management Regulations for Research Projects. | Signature: Liu Fang | Date: June 29, 2024
Institute Leadership Approval | Approved. | Signature: Li Guodong | Date: July 1, 2024
Remarks: After the trip is completed, please submit the complete reimbursement materials within 7 working days, including: this approval form, conference notice, travel invoices (airfare, accommodation receipts, etc.), and work summary. Specific invoice information shall be based on the original invoices.

## Detailed Travel Record
Detailed Travel Itinerary Record
Date | Time Period | Activity | Location (City-level) | Relevance to Project Tasks
2024-07-18 | Full Day | International flight departure and arrival in San Diego | San Diego area, California, USA | Travel preparation for conference attendance
2024-07-19 | Morning | Conference registration and material collection | San Diego area, California, USA | First day of official attendance
2024-07-19 | Afternoon | Attend opening ceremony and keynote presentations | San Diego area, California, USA | Academic exchange
2024-07-19 | Evening | Compile academic notes and prepare presentation materials | San Diego area, California, USA | Conference preparation
2024-07-20 | Morning | Attend thematic seminars | San Diego area, California, USA | Academic exchange
2024-07-20 | Afternoon | Deliver invited presentation | San Diego area, California, USA | Core task: Project outcome reporting
2024-07-20 | Evening | Project progress meeting with Stanford/MIT teams | San Diego area, California, USA | Core task: International cooperation advancement
2024-07-21 | Morning | Attend technical workshop | San Diego area, California, USA | Core task: Equipment and technology research
2024-07-21 | Afternoon | Poster session exchanges and scholar discussions | San Diego area, California, USA | Academic exchange and talent engagement
2024-07-22 | Full Day | Departure and return | San Diego area, California, USA | Return journey
Prepared by: Zhang Mingyuan Date of Preparation: July 24, 2024