## Sheet1
Smart City Data Infrastructure Assessment" Project Washington, D.C. On-Site Survey Itinerary and Budget Breakdown
No. | Date | Day | Planned Work Hours | Main Work Content | Locations Involved (City) | Expense Budget Category | Remarks
1 | 2024-03-10 | Sun | 09:00 - 12:00 | Team arrival, hotel check-in, pre-departure briefing | Washington, D.C. | Accommodation, Local Transportation | Includes airport-to-hotel transportation
2 | 2024-03-10 | Sun | 13:30 - 18:00 | Initial meeting with client; alignment on project background and objectives | Washington, D.C. | Local Transportation | May involve travel to multiple locations
3 | 2024-03-10 | Sun | 19:00 - 21:00 | Working dinner (with client liaison) | Washington, D.C. | Meal Expenses | Requires participant list and business justification
4 | 2024-03-11 | Mon | 09:00 - 17:00 | On-site survey of Data Node Zone A and data documentation | Washington, D.C. | Local Transportation | Survey points are dispersed; frequent vehicle use required
5 | 2024-03-11 | Mon | 20:00 - 22:00 | Internal technical discussion and daily data review | Hotel Meeting Room | None | Internal team work
6 | 2024-03-12 | Tue | 09:00 - 17:00 | On-site survey of Data Node Zone B; interviews with operations personnel | Washington, D.C. | Local Transportation, Meal Expenses | Includes working lunch
7 | 2024-03-12 | Tue | 18:30 - 20:30 | Preliminary solution brainstorming workshop | Washington, D.C. | Local Transportation | May require travel to partner's office
8 | 2024-03-13 | Wed | 09:00 - 16:00 | Supplementary survey and technical detail confirmation | Washington, D.C. | Local Transportation | Fill gaps and verify findings
9 | 2024-03-13 | Wed | 16:30 - 18:00 | Summary meeting with client; presentation of preliminary findings | Washington, D.C. | Local Transportation
10 | 2024-03-13 | Wed | 21:00 - 23:00 | Report drafting and material compilation | Hotel | Meal Expenses (overtime light meal)
11 | 2024-03-14 | Thu | Morning | Finalize report, check out of hotel, travel to airport | Washington, D.C. | Local Transportation