## Cover
2013 Spring Client Reception
Staff Roster & Task Assignments Overview
Key Information
| Event Name: | 2013 Spring Client Reception
| Location: | Sherrybury
| Date: | Early May 2013
| Total Staff: | 23 (21 Internal + 2 External)
| Function Teams: | 6 (Command, Planning, Logistics, Reception, Communications, Technical Support)
Sheet Index
| Sheet Name | Description
| Staff List | Complete staff roster with roles, contacts, and responsibilities
| Duty Schedule | Event day duty assignments by time slot and area
| Team Statistics | Staff count by function team and department distribution
| Level Distribution | Staff distribution by job level
| Key Milestones | Key timeline milestones and completion status

## Staff List
Staff Roster — 2013 Spring Client Reception
No. | Name | English Name | Function | Role | Level | Department | Int/Ext | Ext. | Email | Mobile | Backup | Notes
1 | Liu Ting | Ting Liu | Command | Marketing Director (Event Lead) | Director/Sr. Mgr | Marketing | Internal | 2001 | liu.ting@brightpath.com | (555) 010-2001 | David Brooks | Overall event direction, major decisions, cross-dept resource coordination
2 | — | David Brooks | Command | Sr. Marketing Mgr (Event Deputy Lead) | Director/Sr. Mgr | Marketing | Internal | 2003 | d.brooks@brightpath.com | (555) 010-2003 | Liu Ting | Assist lead with daily prep; act on behalf when lead is absent
3 | — | Sarah Lin | Planning | Marketing Manager (Planning Lead) | Manager/Supervisor | Marketing | Internal | 2010 | s.lin@brightpath.com | (555) 010-2010 | Jessica Wang | Oversee event planning and execution, on-site coordination
4 | — | Jessica Wang | Planning | Marketing Specialist | Specialist/Staff | Marketing | Internal | 2012 | j.wang@brightpath.com | (555) 010-2012 | Kevin Zhang | Event flow design, guest agenda planning
5 | — | Kevin Zhang | Planning | Marketing Specialist | Specialist/Staff | Marketing | Internal | 2014 | k.zhang@brightpath.com | (555) 010-2014 | Sarah Lin | On-site layout planning, vendor coordination
6 | — | Emily Torres | Planning | Marketing Coordinator | Specialist/Staff | Marketing | Internal | 2016 | e.torres@brightpath.com | (555) 010-2016 | Sarah Lin | Materials confirmation and coordination, plan implementation
7 | Wang Ming | Ming Wang | Logistics | Office Admin Supervisor (Logistics Lead) | Manager/Supervisor | Administration | Internal | 3002 | wang.ming@brightpath.com | (555) 010-3002 | Li Zhang | Venue booking, procurement, vendor contract mgmt
8 | Zhang Li | Li Zhang | Logistics | Administrative Assistant | Specialist/Staff | Administration | Internal | 3005 | zhang.li@brightpath.com | (555) 010-3005 | Wang Ming | Materials receipt and on-site setup
9 | — | Rachel Kim | Logistics | Administrative Assistant | Specialist/Staff | Administration | Internal | 3007 | r.kim@brightpath.com | (555) 010-3007 | Thomas Reed | Procurement invoice and document filing
10 | — | Thomas Reed | Logistics | Procurement Clerk | Specialist/Staff | Administration | Internal | 3010 | t.reed@brightpath.com | (555) 010-3010 | Wang Ming | Purchase order follow-up, delivery coordination
11 | — | Hao Chen | Logistics | Facilities Coordinator | Specialist/Staff | Administration | Internal | 3012 | chen.hao@brightpath.com | (555) 010-3012 | Wang Ming | Venue facility liaison, logistics emergency support
12 | — | Amanda Chen | Reception | Client Relations Manager (Reception Lead) | Manager/Supervisor | Marketing | Internal | 2020 | a.chen@brightpath.com | (555) 010-2020 | Michael Li | Guest list, invitation distribution, VIP reception
13 | — | Michael Li | Reception | Client Relations Specialist | Specialist/Staff | Marketing | Internal | 2022 | m.li@brightpath.com | (555) 010-2022 | Amanda Chen | Guest itinerary tracking and coordination
14 | — | Sophia Park | Reception | Client Relations Specialist | Specialist/Staff | Marketing | Internal | 2024 | s.park@brightpath.com | (555) 010-2024 | Amanda Chen | Check-in guidance, guest feedback collection
15 | — | Wan Li | Reception | Executive Assistant to VP | Specialist/Staff | President's Office | Internal | 1005 | li.wan@brightpath.com | (555) 010-1005 | Amanda Chen | One-on-one VIP guest reception
16 | — | Olivia Grant | Reception | Receptionist | Specialist/Staff | Administration | Internal | 3001 | o.grant@brightpath.com | (555) 010-3001 | Sophia Park | Check-in desk on-site service
17 | — | Daniel Wu | Communications | Brand Communications Manager (Comms Lead) | Manager/Supervisor | Marketing | Internal | 2030 | d.wu@brightpath.com | (555) 010-2030 | Jennifer Huang | Visual design, promo materials, comms coordination
18 | — | Jennifer Huang | Communications | Graphic Designer | Specialist/Staff | Marketing | Internal | 2032 | j.huang@brightpath.com | (555) 010-2032 | Daniel Wu | Promotional posters, guest handbook design
19 | — | Ryan Patel | Communications | Content Specialist | Specialist/Staff | Marketing | Internal | 2034 | r.patel@brightpath.com | (555) 010-2034 | Daniel Wu | Annual achievements display materials, post-event PR
20 | — | Chris Nakamura | Communications | Graphic Design Intern | Intern/Temp | Marketing | Internal | 2036 | c.nakamura@brightpath.com | (555) 010-2036 | Jennifer Huang | Design support tasks
21 | — | Alex Rivera | Tech Support | IT Support Specialist (Tech Lead) | Specialist/Staff | IT | Internal | 4005 | a.rivera@brightpath.com | (555) 010-4005 | — | AV/lighting setup, projection equipment, network support
22 | — | — | Tech Support | AV Technician | — | External Vendor | External | — | — | — | Alex Rivera | AV and lighting technical support
23 | — | — | Tech Support | Photographer | — | External Vendor | External | — | — | — | Alex Rivera | Event photography

## Duty Schedule
Event Day Duty Schedule — 2013 Spring Client Reception
Time Slot | Area | Lead | Support Staff | Key Duties | Headcount
08:00—10:00 | Venue Overall | Wang Ming | Zhang Li, Rachel Kim, Thomas Reed, Hao Chen | Final venue inspection, flower and decoration placement confirmation, dining area setup, equipment power-on test | 5
08:00—10:00 | Tech Equipment | Alex Rivera | External AV Technician | Final AV/lighting tuning, projection equipment test, backup equipment in place | 2
10:00—10:30 | Check-in Area | Amanda Chen | Michael Li, Sophia Park, Olivia Grant | Check-in desk setup, guest welcome kits preparation, check-in system test | 4
10:30—11:00 | Full Venue Patrol | Liu Ting, David Brooks | All Team Leads | Final full venue walkthrough, confirm all areas ready status | 8
11:00—14:00 | Check-in & Reception | Amanda Chen | Michael Li, Sophia Park, Wan Li, Olivia Grant | Guest check-in and reception, VIP guest guidance, on-site Q&A | 5
11:00—14:00 | Main Venue | Sarah Lin | Jessica Wang, Kevin Zhang, Emily Torres | Event flow execution, segment transitions, on-site coordination | 4
11:00—14:00 | Dining Area | Wang Ming | Zhang Li | Catering coordination, beverage and refreshment service | 2
11:00—14:00 | Tech Control | Alex Rivera | External AV Technician | Real-time AV/lighting control, presentation switching | 2
11:00—14:00 | Roving Coverage | Daniel Wu | Jennifer Huang, Ryan Patel, Chris Nakamura | Event photography and videography, guest interaction recording, social media real-time updates | 4
14:00—16:00 | Full Venue Wrap-up | All Staff | — | Guest farewell, venue inventory and restoration, materials recovery, equipment return | 23

## Team Statistics
Staff Statistics by Function Team
Function | Team Lead | Internal | External | Total | Department Distribution
Command / Deputy | Liu Ting | 2 | 0 | 2 | Marketing
Planning | Sarah Lin | 4 | 0 | 4 | Marketing
Logistics | Wang Ming | 5 | 0 | 5 | Administration
Reception | Amanda Chen | 5 | 0 | 5 | Marketing, President's Office, Administration
Communications | Daniel Wu | 4 | 0 | 4 | Marketing
Tech Support | Alex Rivera | 1 | 2 | 3 | IT, External Vendor
Total | — | 21 | 2 | 23 | —

## Level Distribution
Staff Distribution by Job Level
Level | Headcount | Personnel List
Director / Senior Manager | 2 | Liu Ting, David Brooks
Manager / Supervisor | 4 | Sarah Lin, Wang Ming, Amanda Chen, Daniel Wu
Specialist / General Staff | 14 | Jessica Wang, Kevin Zhang, Emily Torres, Zhang Li, Rachel Kim, Thomas Reed, Hao Chen, Michael Li, Sophia Park, Wan Li, Olivia Grant, Jennifer Huang, Ryan Patel, Alex Rivera
Intern / Temp Staff | 1 | Chris Nakamura
External Vendor | 2 | External AV Technician, External Photographer
Total | 23 | —

## Key Milestones
Key Milestones — 2013 Spring Client Reception
No. | Milestone Date | Task | Responsible Role | Status
1 | Mar 28, 2013 | Issue event preparation notice | Marketing Department | Completed
2 | Apr 5, 2013 | Complete flowers & decorations procurement plan | Event Prep Team | Completed
3 | Apr 8, 2013 | Submit procurement approval form | Event Prep Team | Completed
4 | Apr 10, 2013 | Procurement approved (Marketing Dir. + VP) | Marketing Dir. + VP | Completed
5 | Apr 10, 2013 | Complete event planning proposal and budget approval | Planning Team | Completed
6 | Apr 12, 2013 | Complete staff roster and task assignments overview | Event Prep Team | Completed
7 | Apr 15, 2013 | Complete guest invitation distribution | Reception Team | Completed
8 | Apr 15, 2013 | Complete vendor confirmation and ordering | Logistics Team | Completed
9 | Apr 20, 2013 | Complete venue booking and vendor confirmation | Logistics Team | Completed
10 | Apr 25, 2013 | Complete materials procurement and layout plan confirmation | Planning & Logistics | Completed
11 | Apr 28–30, 2013 | Flower and decoration delivery and inspection | Logistics Team | Completed
12 | May 1, 2013 | Complete all materials on-site setup | Logistics & Planning | Completed
13 | Early May 2013 | Event officially held | All Staff | Completed
14 | Within 10 working days after event | Complete all expense reimbursement submission | All Team Leads | Completed