## Dispatch Plan
North America Branch Office Preparatory Work Dispatch Plan and Task Assignment
Doc. No.: GIT-PLAN-2018-0315 Prepared: March 12, 2018
I. Project Basic Information
Project Name | North America Branch Office Preparatory Project | Project No. | GIT-NA-2018-001
Dispatch Destination | Frankfort, Kentucky, USA | Region | North America Central
First Dispatch Dates | March 19 - March 23, 2018 | Dispatch Batch | First Batch (Advance Team)
Preparatory Head | Greg Smith (Vice President) | Collaborating Depts. | HR, Finance, Legal
II. Dispatched Personnel and Task Assignment
Name | Title / Position | Primary Tasks | Remarks
Lee Kevin | Vice President (Head of Preparatory Work) | Overall coordination of the Frankfort branch preparatory work, including office site selection, business negotiations, and reporting to headquarters | First batch, on-site throughout
TBD | Admin Supervisor | Assist in arranging temporary office and accommodation, handle local administrative affairs | Second batch
TBD | HR Specialist | Conduct local HR market research and assist in formulating recruitment plans | To be arranged based on progress
III. First Dispatch Timeline (March 19 - March 23, 2018)
Date | Morning Schedule | Afternoon Schedule | Daily Objective
Mar 19 (Mon) | Arrive in Frankfort, KY, USA Check in to temporary accommodation | Familiarize with local environment Initial contact with real estate agents | Complete arrival and initial settlement
Mar 20 (Tue) | On-site visits to candidate office locations (2-3 sites) | Document pros and cons of each site Take on-site photos | Complete preliminary site screening
Mar 21 (Wed) | Meet with local Chamber of Commerce and investment promotion agencies | Consult on legal and tax registration procedures | Understand policies and compliance requirements
Mar 22 (Thu) | In-depth negotiation with landlord of preferred office location | Compile meeting minutes Draft letter of intent | Lock in preferred office location
Mar 23 (Fri) | Local HR market research Visit recruitment service agencies | Write first dispatch work summary Report progress to headquarters | Submit stage work report
IV. Logistics and Accommodation Arrangements
Transportation | International round-trip flights will be booked by the Admin Department. Local transportation will be arranged by the preparatory head based on actual work needs.
Accommodation | During the first dispatch period (March 19 - March 23, 2018), temporary accommodation for the preparatory head will be arranged with assistance from the Admin Department. All expense receipts must be fully retained.
Communications & Equipment | Company laptop and mobile communication devices will be provided to ensure real-time contact with headquarters.
Global Innovation Technologies Inc. Human Resources & Administration March 12, 2018