## Assignment Schedule
Grande Prairie Field Service Assignment – Schedule and Task Log
Ref. No.: GIT-ENG-2012-1008-FS Engineer: Robert Mitchell Client: Northern Energy Solutions Ltd.
Assignment Dates: | October 10 – 11, 2012
Destination: | Grande Prairie, Alberta, Canada
Client Facility: | Northern Energy Solutions Grande Prairie Power Generation Station
Accommodation: | Holiday Inn Express Grande Prairie, 10226 117 Avenue
Date | Time | Activity | Location | Status
Oct 9 | 14:00 | Depart Calgary via corporate shuttle | Calgary Engineering Center | Completed
Oct 9 | 19:30 | Arrive Grande Prairie, initial site survey | Client facility perimeter | Completed
Oct 9 | 21:00 | Check in to Holiday Inn Express Grande Prairie | 10226 117 Avenue | Completed
Oct 10 | 07:30 | Depart hotel for client facility | Holiday Inn Express | Completed
Oct 10 | 08:00 | Full system diagnostic – LM6000 control system | Client control room | Completed
Oct 10 | 12:00 | Lunch break (on-site cafeteria, company account) | Client facility | Completed
Oct 10 | 13:00 | Actuator module replacement – GE-ACT-2204B | Client turbine hall | Completed
Oct 10 | 17:30 | Initial recalibration and parameter verification | Client control room | Completed
Oct 10 | 18:30 | Return to hotel, daily report submission | Holiday Inn Express | Completed
Oct 11 | 07:30 | Depart hotel for client facility | Holiday Inn Express | Completed
Oct 11 | 08:00 | 4-hour continuous load test – varying demand | Client turbine hall | Completed
Oct 11 | 13:00 | Performance metrics review and sign-off | Client conference room | Completed
Oct 11 | 15:00 | Return hotel, pack equipment, check-out | Holiday Inn Express | Completed
Oct 11 | 17:00 | Field service report and certificate submission | Remote to Calgary center | Completed
Oct 12 | 06:00 | Depart Grande Prairie for Calgary | Grande Prairie Airport | Completed
Notes:
1. All on-site work was completed within the planned two-day window. Client sign-off obtained on October 11, 2012 at 14:45.
2. Accommodation: Single occupancy at Holiday Inn Express Grande Prairie, October 10-11, 2012 (1 night). Total: CAD 139.22.
3. Transportation: Calgary-Grande Prairie round-trip via corporate shuttle and return flight. Expenses covered under separate travel voucher.