## Dispatch Plan
North America Branch Office Preparatory Work Dispatch Plan and Task Assignment
North America Branch Office Preparatory Work Dispatch Plan and Task Assignment
Doc. No.: GIT-PLAN-2018-0315 Prepared: March 12, 2018
I. Project Basic Information
Project Name | North America Branch Office Preparatory Project | Project No.
Dispatch Destination | Frankfort, Kentucky, USA | Region
First Dispatch Dates | March 19 - March 22, 2018 | Dispatch Batch
Preparatory Head | Greg Smith (Vice President) | Collaborating Depts.
II. Dispatched Personnel and Task Assignment
Name | Title / Position | Primary Tasks
Lee Kevin | Vice President (Head of Preparatory Work) | Overall coordination of the Frankfort branch preparatory work, including office site selection, business negotiations, and reporting to headquarters
TBD | Admin Supervisor | Assist in arranging temporary office and accommodation, handle local administrative affairs
TBD | HR Specialist | Conduct local HR market research and assist in formulating recruitment plans
III. First Dispatch Timeline (March 19 - March 22, 2018)
Date | Morning Schedule | Afternoon Schedule
Mar 19 (Mon) | Arrive in Frankfort, KY, USA Check in to temporary accommodation | Familiarize with local environment Initial contact with real estate agents
Mar 20 (Tue) | On-site visits to candidate office locations (2-3 sites) | Document pros and cons of each site Take on-site photos
Mar 21 (Wed) | Meet with local Chamber of Commerce and investment promotion agencies | Consult on legal and tax registration procedures
Mar 22 (Thu) | In-depth negotiation with landlord of preferred office location | Compile meeting minutes Draft letter of intent
Mar 23 (Fri) | Return travel to headquarters | Submit first dispatch work summary and progress report remotely
IV. Logistics and Accommodation Arrangements
Transportation: International round-trip flights will be booked by the Admin Department. Local transportation will be arranged by the preparatory head based on actual work needs.
Accommodation: During the first dispatch period (March 19 - March 22, 2018), temporary accommodation for the preparatory head will be arranged with assistance from the Admin Department at the Hampton Inn Frankfort. All expense receipts must be fully retained. March 23 is the return travel day with no local accommodation.
Communications & Equipment: Company laptop and mobile communication devices will be provided to ensure real-time contact with headquarters.