## Transportation Plan
2024 Fall Edmonton Regional Kickoff Event -- Transportation Plan
Ref. No.: GIT-HR-2024-1010-TR Event Date: Oct 17, 2024 Venue: Elk Island Retreat Centre, Fort Saskatchewan
Transportation Coordinator: | David Okafor, Logistics Specialist
Rental Agency: | Budget Rent A Car, Edmonton International Airport
Rental Budget: | CAD 150.00 per day
Time | Activity | Location | Vehicle | Passengers | Cargo
07:30 | Vehicle pickup at Budget counter | Edmonton International Airport | Intermediate SUV | David Okafor (driver) | AV equipment case, 2 boxes
08:00 | Depart airport for downtown pickup | 1000 Airport Road, Edmonton | Intermediate SUV | David Okafor | AV equipment case, 2 boxes
08:30 | Pick up catering containers | Downtown Edmonton catering depot | Intermediate SUV | David Okafor + 1 staff | AV equipment, 2 boxes, 20 lunch boxes
09:00 | Pick up remaining participants | Edmonton Office, 101st Street | Intermediate SUV | David + 3 staff | All cargo loaded
09:45 | Arrive at Elk Island Retreat Centre | 54401 Range Road 203, Fort Sask. | Intermediate SUV | All 4 passengers | Unload cargo
10:00 | Event begins | Elk Island Retreat Centre | - | All participants | -
16:00 | Event concludes, pack up | Elk Island Retreat Centre | Intermediate SUV | David + 3 staff | Reload cargo and equipment
16:45 | Return to Edmonton | Highway 16 West | Intermediate SUV | Same 4 passengers | All cargo
18:00 | Return catering containers | Downtown Edmonton catering depot | Intermediate SUV | David Okafor | Empty containers returned
19:00 | Vehicle return to Budget | Edmonton International Airport | Intermediate SUV | David Okafor | Fuel refill before return